## Gantt Chart
CSE352s — Distributed Online Marketplace ¦ Initial Time Plan ¦ Apr 20 – May 16, 2026
Task | Subteam | 20 M | 21 T | 22 W | 23 T | 24 F | 25 S | 26 S | 27 M | 28 T | 29 W | 30 T | 1 F | 2 S | 3 S | 4 M | 5 T | 6 W | 7 T | 8 F | 9 S | 10 S | 11 M | 12 T | 13 W | 14 T | 15 F | 16 S
|  | April 2026 | [10 empty] | May 2026
PHASE 0 — Team Setup
Create GitHub repo | DevOps
Assign sub-teams & read requirements | All
PHASE 1 — Design (→ Apr 25)
Draw system block diagram | Backend
Draw user flow for all features i–ix | DevOps
UI mockup using Figma for all screens | Frontend
Write architecture justification paragraph for report | DevOps
List all DB entities + draw ER diagram | DB
Write initial schema.sql | DB
Decide & document partitioning strategy per table | DB
Decide which 3 features will be REST/SOAP web services | All
Report: Cover page + Table of Contents + Introduction | DevOps
Report: System Architecture section | DevOps
Report: Distributed DB Design section | DB
Report: Time Plan + task-level Gantt chart | DevOps
Group review of Phase 1 document | All
Submit Phase 1 on LMS | All
SPRINT 1 — Bootstrap + Auth + Account + Items (Apr 25–May 1)
Initialize Spring Boot project | Backend
Initialize React frontend project | Frontend | [7 empty] | `
Set up CockroachDB locally for all backend devs | DB
Finalize api-contract.md before any coding starts | Backend
Finalize schema.sql + write partitioning.sql | DB
Write seed.sql with sample test data | DB
Backend: Auth — register, login, JWT | Backend
Backend: Items — add, edit, remove, list | Backend
Backend: Account — balance, purchased/sold items | Backend
Frontend: Register + Login screens | Frontend
Frontend: Dashboard + Item listing screens | Frontend
Report: Intro + Target Beneficiaries + Tech Stack | DevOps
Report: Role of Each Member + Resources + References | DevOps
Test completed features (Postman) | DevOps
SPRINT 2 — Search + Purchase + Deposit + Inventory (May 2–8)
Backend: Search — text search by name & brand | Backend
Backend: Deposit — add cash to account | Backend
Backend: Purchase — atomic money + item transfer | Backend
Backend: Inventory management | Backend
Backend: Store Interface — REST API for external stores | Backend
Frontend: Search + Purchase screens | Frontend
Frontend: Deposit + Inventory screens | Frontend
Integration: Wire Sprint 1 frontend → backend | DevOps
Test Search endpoints (Postman) | DevOps
Test Deposit endpoints (Postman) | DevOps
Report: Application Level Protocol section | DevOps
Test Purchase flow end-to-end | DevOps
Test Store Interface endpoints | DevOps
SPRINT 3 — Reports + WebServices + Bonus + Testing (May 9–16)
Backend: Reports — transaction reports | Backend
Backend: 3 REST/SOAP Web Services (TBD features) | Backend
Bonus: Feature 1 (TBD) | Backend
Bonus: Feature 2 (TBD) | Backend
Frontend: Reports screen | Frontend
Integration: Full end-to-end wiring & contract fixes | DevOps
Integration: Wire Sprint 2 frontend → backend | DevOps
Report: End-User Guide + screenshots | DevOps
Testing: Backend component tests | Backend
Testing: All API endpoints via Postman | DevOps
Testing: All frontend screens | Frontend
Testing: Full user flow end-to-end | All
PHASE 2 — Documentation & Demo (→ May 16)
Report: Testing section + all test results | DevOps
Update all previously written report sections | DevOps
Build presentation.pptx | DevOps
Write README.txt | Backend
Demo rehearsal as a group | All
ZIP packaging | DevOps
Final submission on LMS | All
LEGEND |  | Phase 0 – Setup |  |  | Phase 1 – Design |  |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Bonus Features |  |  | Weekend |  |  | Today